## Project Budget
Budget: ORRA Online Local Brand
Project Manager: Noha Ibrahem Project Name: ORRA (local online brand) Group Code: NEXT81_ONL1_ERP8_M1d | [6 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | #REF! | #REF! | #REF!
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Design packaging materials
Develop Project Charter | Project Manager | 20 | 250 |  |  |  | 5000 |  | -5000
Conduct Stakeholder Analysis | Project Manager | 10 | 250 |  |  |  | 2500 |  | -2500
Define SMART Goals & OKRs | Project Manager | 10 | 250 |  |  |  | 2500 |  | 10000
Create RACI Chart | Project Manager | 8 | 250 |  |  |  | 2500 |  | -2500
-- | [5 empty] | Total | 12500 | 0
Milestone 2: Product Development
Improve Product Quality | Qualıty Control Manager | 50 | 200 |  |  |  | 6000 |  | 6000
Test Product Quality | Test Product Qualıty | 30 | 200 |  |  |  | 7200 |  | 7200
Design Packaging and Branding | Graphıc Desıgner | 40 | 180 |  |  |  | 1500 |  | 1500
-- | [5 empty] | Total | 14700 | 0
Milestone 3: Marketing Strategy | [8 empty] | 0
Create social media strategy | Socıal medıa Marketıng Specıalıst | 40 | 150 |  |  |  | 6000 |  | -6000
Create Social Media Content | Socıal medıa Marketıng Specıalıst | 60 | 150 |  |  |  | 9000 |  | -9000
Launch Marketing Campaigns | Socıal medıa Marketıng Specıalıst | 80 | 150 |  |  |  | 1200 |  | -1200
Monitor Marketing Campaign Performance | Sales Team | 50 | 160 |  |  |  | 8000 |  | -8000
-- | [5 empty] | Total | 24000 | 0
Milestone 4:Customer Feedback & Engagement | [8 empty] | 0
Conduct Customer Surveys | Customer Support Team | 30 | 120 |  |  |  | 3600 |  | 3600
Implement Feedback Loop | Customer Support Team | 40 | 120 |  |  |  | 4800 |  | 4800
-- | [5 empty] | Total | 2500 | 0
Milestone 5: Sales and Performance Monitoring
Monitor Sales Performance | Sales Team | 30 | 160 |  |  |  | 4800 |  | 4800
Analyze Website Traffic | UI/UX Desıgner | 50 | 200 |  |  |  | 10000 |  | 10000
-- | [5 empty] | Total | 14800 | 0
Milestone 6: Financials
Prepare Financial Reports | Accountant | 20 | 180 |  |  |  | 3600 |  | -3600
Report ROI and Financial Performance | Accountant | 20 | 180 |  |  |  | 3600 |  | 3600
-- | [5 empty] | Total | 12500 | 0
Reserve buffer | [6 empty] | 81000
TOTAL | [6 empty] | #REF! | #REF!