## Comm Plan Exemplar
Project Manager: Noha Ibrahem | ORRA Online Local Brand: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Project Sponsor (Owner) | Project Status Reports | Weekly | Project Manager | Every Thursday | Email, dashboard (Jira, Trello) | Provide project updates, risk alerts, and decisions. | Progress reports, Risk logs | Focus on budget, timeline, and major risks.
Project Team (Designers, Marketing) | Project Meetings/Task Briefings | Twice Weekly | project Manager | Mondays and Wednesdays | Video Conference (Zoom, Meets) | Coordinate tasks, review progress, and resolve issues | Design prototypes, User feedback Branding drafts, Packaging designs Task tracking sheet, Project timeline | Ensure clarity on deliverables and priorities.
Stakeholders (Executive Team) | Executive Progress Reports | Bi-Weekly | Project Manager | 1st and 15th of every month | Email Presentation | Highlight key milestones and potential risks. | Budget reports, Executive summary | Focus on high-level summary and KPIs.
Social Media Marketing Specialist | Social Media Campaign Updates | Weekly | Social Media Manager | Every Monday | Email or slack | Ensure alignment on marketing strategy and progress. | Sales performance and lead report | Include performance metrics.
Sales Team | Sales Performance and Feedback | Monthly | Sales Team manager | End of each month | Email, Inperson Meeting | Review sales data, customer feedback, and market insights. | Sales metrics, Customer data | Align on marketing efforts and sales tactics.
Quality Control Manager | Product Quality Review Meetings | Monthly | QC Manager | First Monday of each month | Inperson Video Conference | Review product quality, discuss improvements | Product quality audit, Customer reviews | Focus on customer satisfaction feedback.
Delivery Team | Logistics and Delivery Updates | Monthly | Delivery Manager | Last Wednesday of each month | Email, video conference | Ensure smooth logistics, address delays, and challenges. | Logistics tracking sheet | Coordinate with sales and product teams.
Customer Support Team | Customer Feedback Review | Bi-Weekly | Customer Support Manager | Every second and fourth Tuesday | Email, slack | Discuss recurring customer issues, feedback, and trends. | Customer satisfaction reports | Focus on service quality and satisfaction.
Accountant/Finance Team | Budget and Financial Reports | Monthly | Accountant | Last Friday of each month | Email, in person Review | Provide financial updates, track budget and expenses. | Budget tracker, Financial forecast | Ensure alignment with project costs.