## Gantt Chart
ORRA Gantt Chart | Project Manager: Noha Ibrahem Project Name: ORRA (local online brand) Group Code: NEXT81_ONL1_ERP8_M1d
[8 empty] | October |  |  |  | November |  |  |  | December
Milestone | ID | Task | Owner | Notes | Start Date | Due date | Duration (days) | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1. Project Planning | 1.1 | Develop Project Charter | Project Manager | Finalize project scope, goals, and stakeholders. | Oct 25. 2024 | 2024-10-27 | 3 | bar: October Week 4
| 1.2 | Conduct Stakeholder Analysis | Project Manager | Identify and assess stakeholders' influence and interest. | Oct 28. 2024 | 2024-10-29 | 2 | bar: October Week 4
| 1.3 | Define SMART Goals & OKRs | Project Manager | Set measurable and actionable goals for the project. | 2024-10-30 | 2024-10-31 | 2 | bar: October Week 4
| 1.4 | Create RACI Chart | Project Manager | Assign roles and responsibilities. | Nov 1,2024 | 2024-11-02 | 2 | bar: November Week 1
2. Product Development | 2.1 | Improve Product Quality | Quality Control Manager | Focus on improving skincare products by changing suppliers. | 2024-11-03 | 2024-11-12 | 10 | bar: November Week 1 to November Week 2
| 2.2 | Test Product Quality | Quality Control Manager | Conduct product testing with quality assurance standards | 2024-11-13 | 2024-11-19 | 7 | bar: November Week 2
| 2.3 | Design Packaging and Branding | Graphic designer | Design new packaging and branding to align with the new product line. | 2024-11-13 | 2024-11-20 | 8 | bar: November Week 2 to November Week 3
3. Marketing Strategy | 3.1 | Create social media strategy | Social Media Marketing Specialist | Outline key marketing strategies and targeted campaigns. | 2021-11-21 | Nov 25,2024 | 5 | bar: November Week 3 to November Week 4
| 3.2 | Create Social Media Content | Social Media Marketing Specialist | Develop content for campaigns across social media platforms. | 2024-11-26 | 2024-12-02 | 7 | bar: November Week 4 to December Week 1
| 3.3 | Launch Marketing Campaigns | Social Media Marketing Specialist | Execute campaigns on social media and digital platforms. | 2024-12-03 | 2024-12-16 | 14 | bar: December Week 1 to December Week 2
| 3.4 | Monitor Marketing Campaign Performance | Sales Team | Track the success of the marketing campaigns. | 2024-12-17 | Ongoing | 365 | bar: December Week 2 to December Week 4
4. Customer Feedback & Engagement | 4.1 | Conduct Customer Surveys | Customer Support Team | Gather feedback from customers on product quality and satisfaction | 2024-12-17 | 2024-12-23 | 7 | bar: December Week 2
| 4.2 | Implement Feedback Loop | Customer Support Team | Use customer feedback to improve products and services. | 2024-12-24 | Ongoing | 365 | bar: December Week 3 to December Week 4
5. Sales and Performance Monitoring | 5.1 | Monitor Sales Performance | Sales Team | Track daily sales performance of new product lines | Dec 17,2024 | Ongoing | 365 | bar: December Week 2 to December Week 4
| 5.2 | Analyze Website Traffic | UI/UX Designer | Use tools like Google Analytics to track user behavior and sales. ¦ | Dec 17,2024 | Ongoing | 365 | bar: December Week 2 to December Week 4
6. Financials | 6.1 | Prepare Financial Reports | Accountant | Track budget allocation and ensure the project remains within budget | 2024-12-01 | Monthly | 30 | bar: December Week 1 to December Week 4
| 6.2 | Report ROI and Financial Performance | Accountant | Present financial success indicators like ROI and profitability | 2021-12-30 | Quartely | 90 | bar: December Week 4