## WBS
ORRA WBS Spreadsheet | Project Manager: Noha Ibrahem Project Name: ORRA (local online brand) Group Code: NEXT81_ONL1_ERP8_M1d
Milestone | ID | Task | Owner | Duration (days) | Notes
1. Project Planning | 1.1 | Develop Project Charter | Project Manager | 3 | Finalize project scope, goals, and stakeholders.
| 1.2 | Conduct Stakeholder Analysis | Project Manager | 2 | Identify and assess stakeholders' influence and interest.
| 1.3 | Define SMART Goals & OKRs | Project Manager | 2 | Set measurable and actionable goals for the project.
| 1.4 | Create RACI Chart | Project Manager | 2 | Assign roles and responsibilities.
2. Product Development | 2.1 | Improve Product Quality | Quality Control Manager | 10 | Focus on improving skincare products by changing suppliers.
| 2.2 | Test Product Quality | Quality Control Manager | 7 | Conduct product testing with quality assurance standards
| 2.3 | Design Packaging and Branding | Graphic designer | 8 | Design new packaging and branding to align with the new product line.
3. Marketing Strategy | 3.1 | Create social media strategy | Social Media Marketing Specialist | 5 | Outline key marketing strategies and targeted campaigns.
| 3.2 | Create Social Media Content | Social Media Marketing Specialist | 7 | Develop content for campaigns across social media platforms.
| 3.3 | Launch Marketing Campaigns | Social Media Marketing Specialist | 14 | Execute campaigns on social media and digital platforms.
| 3.4 | Monitor Marketing Campaign Performance | Sales Team | 365 | Track the success of the marketing campaigns.
4. Customer Feedback & Engagement | 4.1 | Conduct Customer Surveys | Customer Support Team | 7 | Gather feedback from customers on product quality and satisfaction
| 4.2 | Implement Feedback Loop | Customer Support Team | 365 | Use customer feedback to improve products and services.
5. Sales and Performance Monitoring | 5.1 | Monitor Sales Performance | Sales Team | 365 | Track daily sales performance of new product lines
| 5.2 | Analyze Website Traffic | UI/UX Designer | 365 | Use tools like Google Analytics to track user behavior and sales. ¦
6. Financials | 6.1 | Prepare Financial Reports | Accountant | 30 | Track budget allocation and ensure the project remains within budget
| 6.2 | Report ROI and Financial Performance | Accountant | 90 | Present financial success indicators like ROI and profitability